## Sheet1
Sprint Progress Report
Task ID | Task Name | Status | Assigned To | Expected Completion | Comments/Blockers
TASK-1 | Data Collection | Completed | Rakesh | 2025-03-07 | Completed with Dataset
TASK-2 | Data Preprocessing | Completed | Piyush, Rakesh | 2025-03-08 | Completed with Dataset
TASK-3 | Email Filtering (Classification) | In Progress(90% Shippable) | Sathvik, Piyush | 2025-03-13 | Improving the classification feature
TASK-4 | Email Summarization | Backlog | Sathvik, Piyush | TBD | Postponed to Sprint 4